## Slide 1
BigCorp Co. |  |  | Dated: | 2024-09-20
Infiormation Portal Implementation - Phase 1 – Project Summary |  |  | Version: | 1.0
Description of project: |  | Desired outcomes: |  | 
Main project objective is to implement and deliver a customer facing web portal, which addresses all user needs in terms of information related to our company |  | 1. Improved customer satisfaction by 15% 2. Reduced number of call center calls related to our offer by 10% |  | 
In scope | Out of scope | Project progress plan / milestones: |  | 
1. UX Design 2. Software implementation 3. Software testing 4. Content administration | 1. Customer account creation (guest access only) 2. Backoffice integration | 1. Analysis document ready - 2024/10/05 - on track 2. Software ready for testing - 2025/02/10 3. Software testing finished - 2025/03/10 4. Software deployed on production env - 2025/03/24 |  | 
Key project risks |  | Achievements (last week) | Plans (next week) | 
1. Limited software vendor resources 2. Length acceptance process of design and analysis derailing the planned schedule. 3. Inflated stakeholder expectations for the initial scope. |  | 1. meeting regarding initial UX and UI designs 2. Requirements documents created for 30% of functional scope | 1. second iteration on the design 2. At least 60% of documentation for functional requirements ready | 

## Slide 2
BigCorp Co. |  |  | Dated: | 2024-09-20
E-Invoice in Selfservice – Project Summary |  |  | Version: | 1.0
Description of project: |  | Desired outcomes: |  | 
The main project objective is to automate the invoicing process within the self-service portal. This will enhance the efficiency of billing by reducing manual errors and accelerating the payment process. |  | 1. Reduced manual errors by 25% 2. Decreased payment processing time by 40% 3. Enhanced customer experience through automation |  | 
In scope | Out of scope | Project progress plan / milestones: |  | 
1. Automation of invoice generation 2. Integration with payment gateway 3. Real-time invoice tracking | 1. Customer account management 2. Manual invoice generation outside the portal | 1. Initial design document ready - 2024/06/15 - completed 2. API integration with payment gateway - 2024/08/20 - on track 3. User acceptance testing - 2024/11/10 - upcoming |  | 
Key project risks |  | Achievements (last week) | Plans (next week) | 
1. Possible delays in API integration due to third-party dependencies 2. Risk of scope creep if additional features are requested |  | 1. Completed integration with payment gateway 2. Successful testing of invoice generation module | 1. Finalize user training materials 2. Complete user acceptance testing | 

## Slide 3
BigCorp Co. |  |  | Dated: | 2024-09-20
AI-chatbot in Selfservice portal – Project Summary |  |  | Version: | 1.0
Description of project: |  | Desired outcomes: |  | 
The AI-Chatbot project aims to implement a conversational AI system within the self-service portal. The chatbot will assist users with common queries and help streamline customer support. |  | 1. 50% reduction in response time to customer inquiries 2. Increased self-service portal usage by 30% 3. Improved customer satisfaction through real-time query resolution |  | 
In scope | Out of scope | Project progress plan / milestones: |  | 
1. Development of AI-driven chatbot 2. Integration with existing knowledge base 3. Support for text and voice queries | 1. Handling of complex support cases requiring human intervention 2. Multi-language support in phase 1 | 1. Initial AI training completed - 2024/05/20 - completed 2. Integration with self-service portal - 2024/07/30 - on track 3. Beta testing with limited users - 2024/10/15 - upcoming |  | 
Key project risks |  | Achievements (last week) | Plans (next week) | 
1. Potential for AI responses to be inaccurate in rare cases 2. Risk of user pushback if chatbot is not intuitive |  | 1. Successful AI training with 90% accuracy in response generation 2. Positive feedback from early-stage internal testing | 1. Begin beta testing with selected users 2. Refine AI chatbot responses based on user feedback |